## Sheet1
Timesheet - DPM Team 6 Final Project | [10 empty] | Numbers for Formulas
| October 16 - 22 | October 23 - 29 | October 30 - November 5 | November 6 - 12 | November 13 - 19 | November 20 - 26 | November 27 - December 1 (Documentation) |  |  |  | Alotted Hours per Member | 58.5
Group Member | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Hours Remaining | Total Hours Worked | Legend | Total Project Hours | 351
Frederic Cyr | 7 | 9 | 10 | 8.5 | 4 | 9 | 2 | 9 | 49.5 | At least 10% above average working hours
Alex Hale | 6 | 5.5 | 10.5 | 1 | 11.5 | 12 | 13 | -1 | 59.5 | At least 10% below average working hours
Joshua Inscoe | 6.5 | 5 | 8 | 4 | 15.5 | 20.5 | 3 | -4 | 62.5 | At least 20% below average working hours
Justin Tremblay | 2 | 6 | 8 | 10 | 8 | 10 | 7 | 7.5 | 51
Xu Hai (Mike) | 10 | 7.5 | 11 | 8.5 | 8 | 8.5 | 1 | 4 | 54.5
Xianyi Zhan (Jeffrey) | 8 | 6.5 | 7.5 | 5.5 | 9 | 10 | 3 | 9 | 49.5
Totals | 39.5 | 39.5 | 55 | 37.5 | 56 | 70 | 29 | 24.5 | 326.5
Frederic Cyr | 7 hours were spent on HW design (04), finding the 3 alternatives (09, 10), and writing the HW documentation (11). | 4 hours were spent building the robot for final project (13), 2 hours were spent on sketches (09), and 3 hours were spent updating the hardware document (14). | 4.5 hours were spent on building the new robot (21), 0.5 hour sketching the free-body diagram (19-C), 2 hours testing the hardware (22), 3 hours writing the hardware and testing documents (23, 40). | 4 hours on adding the funnels to the zipline wheel (40-A), 3.5 hours sketching the robot with LDD program (40-B), 0.5 hour on testing (42) and figuring out integration test instructions, and 0.5 hour on writing info on hardware document (40-C). | 1.5 hour spent on finalizing the LDD sketch for poster presentation (45), 1.5 hour spent on updating the hardware document (40-C), 1 hour spent making the funnels more solid and testing it on the zipline (34, 40-A). | 1 hour on new zipline margin error testing (34), 1 hour spent on writing test document (44), 1 hour spent to help with the poster presentation (45), 6 hours on testing final competation, avoidance, research and other extreme cases (50) | Spent 2 hours assisting with final document submission (54).
Alex Hale | 6 hours were spent on creating the week 2 meeting presentation (08), the HW/SW/Testing documentation (04, 05, 06), and transitioning everything to Google Drive (08). | Spent 1 hour finalizing meeting #2 documentation (08), 3 hours reviewing and upgrading documentation from other team members and previous weeks (14, 19), and 1.5 hours preparing documentation for meeting #3 (19-A). | Spent 3 hours writing the Zipline controller (33) and merging the sensor pollers into one thread (18), 2.25 hours preparing meeting #4 documents (23-A), and 5.25 hours updating ongoing documentation with images and new information (23, 39, 40). | Spent 1 hour finalizing Meeting #4 documentation (23-A). | Spent 7 hours creating poster for presentation (45) and 4.5 hours preparing the Week 6 documents for submission (48-B). | Spent 9 hours creating the presentation poster (45), 1 hour preparing the presentation script (53-A) and competition checklist (53-A), and 2 hours preparing documentation for pre-competition submission (52, 53). | Spent 8 hours preparing the final project report and 5 hours preparing other documents for submission (54).
Joshua Inscoe | 6.5 hours were spent adjusting the GANTT Chart and budgets (07). | 4 hours were spent outlining software class interfaces (17, 19) and 1 hour was spent updating the GANTT chart (12). | 8 hours were spent overhauling the GANTT Chart and updating the budget (19-B). | 4 hours were spent updating the new version of the SensorData class to work with all sensors (41). | 14 hours were spent on designing and implementing the search algorithm (35), and 1.5 hours were spent matching reported work on the Timesheets to individual tasks in the GANTT Chart (44-A). | 6.5 hours were spent working further on the search algorithm (35), 10.5 on writing / performing tests for the search algorithm (36), 1.5 hours preparing for final project presentation (53-A), and 2 hours on further testing of the searcher algorithm and other software (36). | 3 hours spent updating the GANTT Chart and budget (54) and matching tasks in the GANTT Chart to those in the Timesheet (54).
Justin Tremblay | 2 hours were spent on the software design documentation (05), while other working hours were spent on Lab 5 software. | 2 hours were spent restructuring the software archtecture (16), 3 hours were spent updating the software design document (14), and 1 hour was spent writing an API with Javadoc (19). | 6 hours were spent on reimplementing the localization (29, 31) and navigation systems (27). 1 hour was spent on implementing the wifi code into the main controller (37), 1 hour on troubleshooting various issues (37). | 3 hours spent on WIFI integration and path planning (41), 6 hours spent on integration (37) and optimization for beta demo (41) and 1 hour spent on writing testing scripts for the testing team (42). | 5 hours spent finalizing the software design document (52). 3 hours spent on making adjustment to the software. (48) | 10 hours on finalizing software for the robot (48) | 4 hours spent on finalizing the software design document (54), 2 hours spent cleaning code base (54), 1 hour spent on javadocs (54)
Xu Hai (Mike) | Spent 6 hours on hardware design (04), 3 hours on testing (10), and 1 hour on testing documentation (06). | 3 hours were spent building the robot for the final project (13), 3 hours were spent testing the robot (14-A), and 1.5 hours were spent updating the testing document (14). | 9 hours on testing motors (22), sensors (22), zipline crossing and software (26, 28, 30, 32, 34), 2 hours on test document (40) | 6 hours on testing (42), 1 hour on preparing integration test (42), 0.5 hour on analyzing data, 1 hour updating test document (44) | 4 hours on testing the improvement from beta demo (49), 1 hour on data analyzing, 3 hours on graph making (53) and writing test document (53) | 1 hour on new zipline margin error testing (34), 1.5 hours on testing document writing and graph making (53), 6 hours on testing final competition (50), research and other extreme cases. | 1 hour on graph-making and writing the test document (54)
Xianyi Zhan (Jeffrey) | Spent 1 hour learning to use Lego Digital Designer, 3 hours on hardware design (04), 3 hours on testing (10), and 1 hour on testing documentation (06). | 2.5 hours were spent testing the previous version of the robot (10), 1 hour was spent updating the testing document (14-B), 2 hours were spent building the robot for the final project (13), and 1 hour was spent testing the final project robot (14-A). | 4 hours were spent testing the motors and sensors of the final project robot (22), 3.5 hours were spent on writing testing document based on tests of this week (40). | 4.5 hours spent on testing (42) and figuring out integration test instructions, 1 hour spent on collecting data and writing test document (44). | 4 hours on testing the adjustment from beta demo (49), 1 hour on data analyzing, 2.5 hours on wrting test document (53), 1.5 hours on updating test plan (20). | 1 hour on new zipline margin error testing (34), 2 hours on research and other cases (50), 5 hours on final competition testing (50), 2 hours on test document (53) | Spent 3 hours assisting with final document submission (54).